## Sheet1
Requirements Formalization | Nick | Ryan | Brian | Joe
Research and Learn Biological Process | 25 | 25 | 25 | 25
Discuss with Customer | 25 | 25 | 25 | 25
Refine Knowledge as Needed | 25 | 25 | 25 | 25
GUI Framework | Nick | Ryan | Brian | Joe
Research Tools (QT, WXPython, etc) | 25 | 25 | 25 | 25
Design GUI |  | 50 |  | 50
Build GUI |  | 50 |  | 50
Build Base Epithelium Example | Nick | Ryan | Brian | Joe
Create Cell Class |  |  | 50 | 50
Create Epithelium Class |  |  | 50 | 50
Particle Cell Collision |  |  |  | 100
Visual Check | 50 | 50
Epithelium Development | Nick | Ryan | Brian | Joe
Define and Implement Cell Properties |  | 50 |  | 50
Meet with Customer | 25 | 25 | 25 | 25
Visual Check | 50 | 50
Furrow Implementation | Nick | Ryan | Brian | Joe
Implement Supporting Data Structures | 50 |  | 50
Meet with Customer | 25 | 25 | 25 | 25
Visual Check | 50 | 50
Ommatidium Formation | Nick | Ryan | Brian | Joe
Implement Properties of Ommatidium | 50 |  | 50
Meet with Customer | 25 | 25 | 25 | 25
Presentation and Rules Check | Nick | Ryan | Brian | Joe
Formally Present a Completed MVP | 25 | 25 | 25 | 25
Check Rules of Objects in Simulation | 25 | 25 | 25 | 25
Refine As Needed | 25 | 25 | 25 | 25
Implementation of Additional Goals Past MVP | Nick | Ryan | Brian | Joe
Implement Saving Configurations | 100
Import/Export Options | 50 |  |  | 50
Automated Documentation |  | 50 | 50
Restful Interface Implementation | 50 |  |  | 50